## Sheet1
Week | Backend | Time
2021-07-03 | Create Trello Board | 1
14/3/2021 | Build Project Scaffold | 3
21/3/2021 | Set Up Azure Cloud Shell | 1
28/3/2021 | CI with GitHub Actions | 2
2021-04-04 | Build API Skeleton | 1
2021-11-04 | CD with Azure Pipelines | 2
18/4/2021 | Perform Predictions | 3
25/4/2021 | Create Documentation | 2
2021-02-05 | Create Video Demo | 2
2021-09-05 | Backend ready for QA | 5
16/5/2021
23/5/2021
Goals
Deployed on Azure
Perform predictions
Flask API
Documentation